OSTRO / WORKING TEMPLATES

# Branding proposal

Completed example · fictional details and illustrative amounts

Prepared by: Example Studio
Prepared for: Example Company
Date: 1 September 2026

## Project summary

Create a consistent identity for a small business expanding its services.

## Objectives and success criteria

The final identity is supplied in the agreed file formats with clear rules for its intended uses.

## Deliverables

One primary logo and two variations
Color palette and typography choices
A concise brand usage guide
Exported digital artwork

## Out of scope

Naming, trademark searches, packaging production and printed materials.

## Timeline and milestones

Week 1: discovery and creative direction
Week 2: identity concepts
Week 3: refinements and final artwork

## Client responsibilities

Business background, intended audience, existing assets and a single person responsible for final feedback.

## Commercial terms

Illustrative project fee: USD 1800. Example payment schedule: 50% at acceptance and 50% before handover. Replace this with your agreed currency, price and terms.

## Revisions and next steps

Two consolidated review rounds are included in this example. Additional work requires written agreement on scope, price and timing. Confirm acceptance before work begins.

## Before sending — remove this checklist

• Replace the example scope with the actual client requirements.

• Agree on included revisions, responsibilities and approval timing.

• Review the price, schedule and acceptance process before sending.

Template and example: https://tryostro.com/templates/branding-proposal/