OSTRO / WORKING TEMPLATES

# Marketing project brief

Completed example · fictional details and illustrative amounts

Prepared by: Example Studio
Prepared for: Example Company
Date: 1 September 2026

## Background and problem

Prepare and run a four-week campaign to introduce a new service to an existing audience.

## Audience

Existing customers and prospective buyers who need a clear, usable experience. Replace this with the specific people the project serves.

## Desired outcome

The agreed content is delivered or published and results are reported using the selected attribution method.

## Required outputs

Campaign messaging and content plan
Four email drafts and eight social posts
Tracking-link naming sheet
A campaign results summary

## Available inputs

Offer details, approved claims, brand assets, audience access permissions and a feedback contact.

## Constraints and exclusions

Advertising spend, video production, purchased contact lists and ongoing campaigns.

## Timing and approvals

Week 1: messaging and campaign plan
Week 2: content drafts and review
Weeks 3–4: agreed publishing schedule
End of week 4: results summary
One nominated project owner will consolidate feedback at each stage.

## Open questions

Confirm the budget range, internal review availability, final delivery formats and any dependencies before commissioning the work.

## Before sending — remove this checklist

• Name the person responsible for decisions and consolidated feedback.

• Separate requirements from preferences and unresolved questions.

• Confirm dates and dependencies before treating them as commitments.

Template and example: https://tryostro.com/templates/marketing-brief/