OSTRO / WORKING TEMPLATES
Marketing proposal
Completed example · fictional details and illustrative amounts
Prepared by: Example Studio
Prepared for: Example Company
Date: 1 September 2026
Project summary
Prepare and run a four-week campaign to introduce a new service to an existing audience.
Objectives and success criteria
The agreed content is delivered or published and results are reported using the selected attribution method.
Deliverables
Campaign messaging and content plan
Four email drafts and eight social posts
Tracking-link naming sheet
A campaign results summary
Out of scope
Advertising spend, video production, purchased contact lists and ongoing campaigns.
Timeline and milestones
Week 1: messaging and campaign plan
Week 2: content drafts and review
Weeks 3–4: agreed publishing schedule
End of week 4: results summary
Client responsibilities
Offer details, approved claims, brand assets, audience access permissions and a feedback contact.
Commercial terms
Illustrative project fee: USD 1600. Example payment schedule: 50% at acceptance and 50% before handover. Replace this with your agreed currency, price and terms.
Revisions and next steps
Two consolidated review rounds are included in this example. Additional work requires written agreement on scope, price and timing. Confirm acceptance before work begins.
Before sending — remove this checklist
• Replace the example scope with the actual client requirements.
• Agree on included revisions, responsibilities and approval timing.
• Review the price, schedule and acceptance process before sending.
Template and example: https://tryostro.com/templates/marketing-proposal/
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