OSTRO / WORKING TEMPLATES

# Marketing proposal

Completed example · fictional details and illustrative amounts

Prepared by: Example Studio
Prepared for: Example Company
Date: 1 September 2026

## Project summary

Prepare and run a four-week campaign to introduce a new service to an existing audience.

## Objectives and success criteria

The agreed content is delivered or published and results are reported using the selected attribution method.

## Deliverables

Campaign messaging and content plan
Four email drafts and eight social posts
Tracking-link naming sheet
A campaign results summary

## Out of scope

Advertising spend, video production, purchased contact lists and ongoing campaigns.

## Timeline and milestones

Week 1: messaging and campaign plan
Week 2: content drafts and review
Weeks 3–4: agreed publishing schedule
End of week 4: results summary

## Client responsibilities

Offer details, approved claims, brand assets, audience access permissions and a feedback contact.

## Commercial terms

Illustrative project fee: USD 1600. Example payment schedule: 50% at acceptance and 50% before handover. Replace this with your agreed currency, price and terms.

## Revisions and next steps

Two consolidated review rounds are included in this example. Additional work requires written agreement on scope, price and timing. Confirm acceptance before work begins.

## Before sending — remove this checklist

• Replace the example scope with the actual client requirements.

• Agree on included revisions, responsibilities and approval timing.

• Review the price, schedule and acceptance process before sending.

Template and example: https://tryostro.com/templates/marketing-proposal/