## Instructions
Project budget template
Completed example — fictional entries in USD
Use this before a project starts, then update the actual-cost column as work progresses. Keeping scope and costs together helps identify where assumptions changed.
Start on Summary: set your currency label. For the invoice tracker, also set the as-of date.
Enter your records in the pale-blue cells on Entries. Pale-green cells contain formulas.
The workbook has 200 entry rows (rows 2–201). Extend ALL formulas and summary ranges before adding more.
Use one currency per workbook. No exchange-rate conversion is performed.
Open in Microsoft Excel, or upload a copy to Google Sheets. Enable automatic calculation in your spreadsheet app.
No macros, external data connections or online account are required.
Keep planned and actual amounts on the same tax basis.
Use one currency throughout the workbook.
Set your own contingency; the example percentage is illustrative.
Budget lines
Category, cost item, planned cost, actual cost and remaining budget.
Variance convention
Remaining budget is planned minus actual. A negative value means the line is over its planned budget.
Summary
The workbook totals planned and actual costs and calculates an optional contingency on the planned total. The contingency is not counted as an incurred expense.
https://tryostro.com/templates/project-budget/

## Summary
Project budget template
Currency label | USD
Contingency rate | 10%
Planned costs | 5000
Actual costs | 4650
Remaining before contingency | 350
Contingency allowance | 500
Plan including contingency | 5500
Remaining including contingency | 850

## Entries
Category | Cost item | Planned | Actual | Remaining
Design | Design and production | 1800 | 1950 | -150
Development | Website build | 2400 | 2100 | 300
Content | Copy and illustrations | 800 | 600 | 200